## G1S1
PROJECT PLAN TEMPLATE
Organizational Unit | Division of Chemical Health & Safety (CHAS)
Kickoff Date | 2023-11-01
Goal 1 | Cultivate Community. Establish and implement a framework and infrastructure to recruit, onboard, mentor, retain members, and foster internal and external collaborations.
Goal 1 Strategy 1 | Evaluate current governance and committee structure and subsequently restructure in alignment with the strategic plan within the next 6 months.
Impact__Resources__ | Impact, H; Resources, M
Target Completion Date | 2024-06-01
Champions | Sammye Sigmann
Proposed Team Lead | Sammye Sigmann
Other Proposed Team Members | Jack Reidy
Kimi Brown
Russ Phifer
Kali Miller
Mary Beth Koza
Stakeholders Served: | CHAS
Target Audiences: | CHAS
Strengths or Opportunities Leveraged: | Utilizing our members effectively
Component Task or Decision | Success Metric | Person Responsible | By When
Map current committees and include function, chair, members | Fairly easy to do using known information | Sammye | October/November 2023
Team members meet to discuss current structure and how it can or cannot support CHAS and SP | Meeting occurs | Team above and any others interested (within reason) | 2023-11-01
Followup meetings as needed | Report prepared for EC | Team above and any others interested (within reason) | 2023-12-01
Recommendations to EC | EC accepts team assessment or | Team above and any others interested (within reason) | 2024-01-01
Reevaluate structure plan | EC accepts team assessment |  | 2024-03-01
Critical Success Factors
1 | People that take on committee responsibilities follow through with their obligations.
2 | The committees support the desired outcomes for the division
3
4
Barriers to Implementation and Ways To Overcome
1 | Change resistance. Can be overcome by making a solid case for populating the committees and positions needed to advance and monitor the high priority projects
2 | Lack of involvement. Make sure there is ownership and support
3
4
Resources Needed and Where They Can Be Obtained
1 | No money required. Just member time.
2
3
4
Management Accountability
1 | Check in system?
2
3
4
Other Notes
Many of the other Goal/Strategies depend upon getting this accomplished.
If others see particular needs for infrastructure, these should be forwarded to this Project Lead and Team.

## G1S2
PROJECT PLAN TEMPLATE
Organizational Unit | Division of Chemical Health and Safety
Kickoff Date | 2023-09-06
Goal_1_ | Cultivate Community: Establish and implement a framework and infrastructure to recruit, onboard, mentor, and retain members, and foster internal and external collaborations.
Goal _1 Strategy _2 | Establish CHAS Communities program including charters and leadership guide within 6 months.
Impact__Resources__ | I:H, R:M
Target Completion Date | 2024-04-01
Champions | Robin Izzo & Kimi Brown
Proposed Team Lead | Robin Izzo
Other Proposed Team Members | Kristi Ohr
Dwayne Henry
Debbie Decker
Jim Tung
Amy Moore
Kimi Brown
Stakeholders Served: | CHAS members, ACS members, LST community, EHS personnel, laboratory researchers, educators, students, chemical professionals
Target Audiences: | All stakeholders
Strengths or Opportunities Leveraged: | Member attributes, leadership, virtual communication, emerging technologies
Component Task or Decision | Success Metric | Person Responsible | By When
Using the results of the CHAS Communities survey, choose 3-5 Communities and identify potential leaders and/or facilitators. | 3-5 CHAS Communities presented to EC |  | 2023-11-01
Create a template for CHAS Community charters, roadmap, toolbox. | Resources completed and ready for distribution. |  | 2024-01-01
Determine appropriate CHAS committee infrastructure to support CHAS Communities. | EC approval of any potential changes |  | 2024-01-01
Choose and implement an interim communication and information sharing option (e.g., Basecamp, Listserv, Slack, etc.) | Option(s) chosen and ready for use |  | 2024-01-01
Market the new CHAS Communities. Hold first Zoom meeting with each. | Each CHAS Community has held an initial, forming meeting. |  | 2024-02-01
Develop charters that include governance (e.g., role of leaders, term, etc.), purpose, communication methods, meeting protocols, goals and objectives, etc. | Charters complete, reviewed by task force |  | 2024-05-01
Select CHAS Community leaders. | Charters include the name of each leader. Leaders have been onboarded by representative of the task force. |  | 2024-05-01
Monitor activities of CHAS Communities (e.g., freqency of meetings, outputs, etc.) | CHAS Communities are meeting the expectations set in their respective charters. |  | Ongoing
At least annually, determine whether to add, remove, or combine Communities. | Annual report to EC (verbal or in writing) |  | Ongoing
When the new CHAS communications platform(s) are complete, transition from the temporary platforms. | All CHAS Communities are using the CHAS communications platforms. |  | Dependent on G1S3
Critical Success Factors
1 | 3-5 CHAS Communities are actively communicating and sharing
2 | Participants find value in engagement
3 | CHAS Communities are recommending or producing symposia, workshops, CHAS Chats, webinars, and other resources
4
Barriers to Implementation and Ways To Overcome
1 | Continuity of leadership of each community | Task force or assigned committee will monitor
2 | Volunteer degradation | Continued marketing of value, review and restructuring, as needed
3 | Limited resources for support | Start small and add incrementally
4 | Dissatisfaction in communications methods | Review and adjust as possible
Resources Needed and Where They Can Be Obtained
1 | Volunteers | CHAS members
2 | Temporary communications options | Princeton for listerv lists, CHAS for Basecamp
3
4
Management Accountability
1 | Task force or assigned committee provides updates to EC at each meeting - standing agenda item
2 | Task force tracks activity and follows up as needed
3 | Each Community provides a short activity summary at national meetings
4
Other Notes
Need volunteers to draft issurances
Does Cann have a community to be part of this effort? [journal club, webpage]
Want this to be inclusive.

## G1S3
PROJECT PLAN TEMPLATE | Communication for CHAS
Organizational Unit | Web Presence Ad-Hoc Committee, Website and Email Administrator or CHAS
Kickoff Date | 2023-10-01
Goal_1_ | Establish and implement a framework and infrastructure to recruit, onboard, mentor, retain members, and foster internal and external collaborations
Goal _1 Strategy _3 | Build a communication network that incorporates email, webpage, and social media, and targets the division as a whole, CHAS communities, ACS members, and the general public.
Impact__Resources__ | I: H, R: H
Target Completion Date | 2025-02-01
Champions | Robin Izzo, Calla McCulley
Proposed Team Lead | Website and Email Administrator of CHAS
Other Proposed Team Members | Jack Reidy
Calla McCulley
Melinda Box
Three additional members actively involved in CHAS
*recruit on LISTSERV*
Stakeholders Served: | CHAS members, LST community, ACS members, EH&S personnel, lab researchers, chem educators, students, and chem professionals
Target Audiences: | All stakeholders
Strengths or Opportunities Leveraged: | Leadership, Virtual Communication, Emerging technologies, and partnerships
Component Task or Decision | Success Metric | Person Responsible | By When
Complete internal needs assessment for all forms of communication (website, email, social media) | Completed report |  | Spring 2024
Determine appropriate committee infrastructure to support these functions (repeat as needed) | EC approval of any potential restructure(s) |  | Spring 2024 (as needed afterwards)
Determine website platform and associated costs | EC approval of chosen platform |  | Fall 2024
Decide on communication platforms that will be used for the various audiences we plan to have an interface with | EC approval of chosen platform |  | Fall 2024
Acquire necessary funding (could partner to ask for support) | EC approval of cost from budget |  | Spring 2025
Create a content team | Met with content team |  | Spring 2025
Redesign website | Website is launched |  | 2026-01-01
Implement selected communication platforms | Communication platforms are launched |  | 2026-01-01
Create marketing plan(s) for various communication forms | Track utilization (number of hits per platform) over time |  | 2026-01-01
Utilize content team to implement and maintain systems and content | Content is being updated regularly |  | Ongoing
User feedback | Completed report from survey results |  | Summer 2026
Critical Success Factors
1 | Successful redesign of website
2 | Increased communication pathways between various stakeholders
3 | Positive user feedback
4 | Continuity of content team
5 | Demonstration of new content being posted regularly
Barriers to Implementation and Ways To Overcome
1 | Lack of consensus | 80:20 rule
2 | Funding | Use existing resources, choose lower cost options
3 | Volunteer degradation | Marketing
4 | Refusal to use/resistance to change | Education, persistence, ensuring new platforms can function in familiar ways
Resources Needed and Where They Can Be Obtained
1 | Volunteers - in CHAS
2 | Funding - through CHAS, ACS, and ACS external partners
3 | System Candidates - word of mouth, email, recommendations, and testing
4
Management Accountability
1 | Content team meeting regularly to perform functions
2 | Project Team tracks and ensures forward progress
3 | Pay particular attendance to content team composition
4 | Need peer review of what is posted on website
Other Notes
Connection with G2S3, G1S2
Connect with Rob Toreki
web needs to be ADA compliant

## G1S4
Organizational Unit | Division of Chemical Health and Safety
Kickoff Date | 2023-09-21
Goal 1: Cultivate Community | Establish and implement a framework and infrastructure to recruit, onboard, mentor, retain members, and foster internal and external collaborations.
Goal 1 Strategy 4 | Attract new members by clearly defining CHAS Value Propositions and engage them with a formal onboarding process
Impact/Resources | Impact: M; Resources: M
Target Completion Date | 2023-09-21
Champions | Jack Reidy, Kimi Brown
Proposed Team Lead | Membership Chairperson (Jack Reidy
Other Proposed Team Members | Anthony Appleton
TBD
TBD
TBD
TBD
recruit on LISTSERV
Stakeholders Served: | CHAS Members
Target Audiences: | New CHAS Members; non-CHAS ACS members
Strengths or Opportunities Leveraged: | Membership attributes; virtual communications
Component Task or Decision | Success Metric | Person Responsible | By When
Assemble a holistic list of CHAS membership benefits | A comprehensive list of member benefits is submitted to and agreed upon by the Executive Committee by the target date.
Craft standard language of CHAS benefits for use on our website, in emails, at ACS meetings, etc. | By the target date, one clear, concise, broadly applicable paragraph explaining benefits of joining CHAS is posted to the CHAS website, and included in membership committee documentation with suggestions for how and where it shall be used.
Create tailored language of CHAS benefits targeted at specific audiences (e.g., graduate students, industry professionals) | Membership benefit language samples targeted for 5 different audiences
Create a list of volunteering opportunities/current needs including identifying who (which role) is responsible for keeping the list up to date and a schedule for review and update. | The list of volunteering opportunities is compiled, and posted on the CHAS website, and is scheduled for desemination to CHAS membership via email at least quarterly.
Create a document charting the workflow of the onboarding process. | Document is completed and included with membership committee documentation in Basecamp or other division file management system. | Jack Reidy
Recruit members for the Membership Committee | At least 3 volunteers recruited from outside the EC/strategic planning group
Create a "Welcome Wagon" volunteer team to reach out to new members, including written guidelines and expectations for the team members. | At least 3 volunteers recruited from outside the EC/strategic planning group (can be same people as in tactic above)
Critical Success Factors
Motivated, responsive volunteers (including current committee chairs)
Responsive management of the division website content
Barriers to Implementation and Ways To Overcome
Lack of volunteers | Contact personal connections to find potential volunteers who aren't overloaded
Lack of clearly defined volunteer roles | Accountability from EC; worst case, 1-on-1 meetings with committee chairs
Resources Needed and Where They Can Be Obtained
Volunteers | CHAS
Management Accountability
Membership Committee
Other Notes
Calla is interested in discussing about the Welcome Wagon
ACS Staff has responsibility for transmitting contacts at meetings.
Look at correlation with G1S3

## G2S1
PROJECT PLAN TEMPLATE
Organizational Unit
Kickoff Date | 2023-11-01
Goal_2_ | Goal 2: Communicate Best Safety Practices. Through technical programming, education, recognition, and outreach, advance and communicate best safety practices and their value.
Goal _2 Strategy _1 | G2S1: By 2025, expand technical programming through co-sponsorship of symposia with other Divisions.
Impact__Resources__ | Impact: High Resources: Medium
Target Completion Date | Develop infrastructure by Fall 2025 (to match with Future of Meetings goal from ACS Leadership). This would be ongoing into the future and should probably be a perpetual goal. | should be ongoing
Champions | Debbie Decker; Mary Beth Koza
Proposed Team Lead | Debbie Decker
Other Proposed Team Members | Monique Wilhelm
Russ Phifer
Joe Pickel
Mary Beth Koza
Frankie Wood-Black
Stakeholders Served: | CHAS membership
Target Audiences: | ACS
Strengths or Opportunities Leveraged: | Excellent symposia organizers and speakers. Creative ideas to present content. Existing relationships with several divisions already
Component Task or Decision | Success Metric | Person Responsible | By When
Attend Future of Meetings Workshop | meeting attendance | Debbie | 2024-01-01
Create list of Divisions for collaborative co-sponsorship of symposia | list creation & IPG grant | EC CHAS | 2024-06-01
Create list of Divisions/local secrions for outreach for programing | list creation | EC CHAS | 2023-06-24
Based on FoM workshop and input from ACS leadership, develop innovative programming ideas | develop list of innovative programming ideas | Debbie/MBK | 2023-06-24
Implement innovative programming | # of innovative programming | Debbie | 2025-01-01
Develop pre-programmed symposia for Regional Meetings or other Division programs | Participation at regional meetings | Mark | 2024-06-01
Work across CHAS committees to identify awards and recognition | number of new awards | CHAS EC | 2024-01-01
Identify symposia that meet this goal and track attendance and report back to EC. | Symposia Attendance | MBK/Deb | Spring 2-24
Critical Success Factors
1
2
3
4
Barriers to Implementation and Ways To Overcome
1
2
3
4
Resources Needed and Where They Can Be Obtained
1
2
3
4
Management Accountability
1
2
3
4
Other Notes
CCS Partnership Subcommittee might be a potential partner here?
Use the "Welcome Wagon" idea here?
"Symposium in a Box" idea? Similar to what LSAC has done.

## G2S2
PROJECT PLAN TEMPLATE
Organizational Unit | Write Organozational Unit Name Here
Kickoff Date | Write Date Here
Goal__2 | Goal 2: Communicate Best Safety Practices. Through technical programming, education, recognition, and outreach, advance and communicate best safety practices and their value.
Goal _2 Strategy _2 | G2S2: By the end of 2024, work collaboratively with national ACS, CCS, ACS Publications, ACS Chemical Health and Safety, and Chemical Abstract Services, to implement best practices and amplify health and safety resources using databases, e-publications, and web presence.
Impact__Resources__ | I,H; R,L.
Target Completion Date | 2024-12-31
Champions | Michael G. Koehler & Marta Gmurczyk
Proposed Team Lead | Michael G. Koehler or appropriate designate
Other Proposed Team Members | Mary Beth Mulcahy (ACS CH&S)
Others from the Envisioning the Future of ACS Chemical Health and Safety - TBD
Sammye
Write Member 4 Here
Write Member 5 Here
Stakeholders Served: | CHAS Members, ACS Members, EH&S Professionals, Chem Students, Chem Professionals
Target Audiences: | CHAS Members, ACS Members, EH&S Professionals, Chem Students, Chem Professionals
Strengths or Opportunities Leveraged: | Virtual Communication, Emerging Technologies.
Component Task or Decision | Success Metric | Person Responsible | By When
Task 1: Communicate the output from the Strategic Plan with Envisioning the Future of ACS Chemical Safety Team | 1. Output of this workshop has been documented and distributed to others in Envisioning Workshop. 2. A Follow-Up ZOOM meeting is offered for others who did not participate in this Strategic Planning Workshop.
Task 2: Conducts an inventory of current health and safety communication resources, including but not limited to databases, e-publications, and web presence. | 1. Inventory list which has been harmonized with others involved in Health and Safety communications.
Task 3: Develop a "Wish List" of desired communication resources which would support the Goal. | A wish list of communication resources.
Task 4: Conduct a GAP ANALYSIS which prioritizes improvements opportunities to CLOSE THE GAP. | A GAP analysis which prioritized communication resources.
Task 5: Develop an implementation strategy for the improvement opportunities. | Documented implementaton plan
Task 6: Implement opportunities and lock in the gains. | Number of implemented improvements. GAP Analysis score improvement.
Task 8: Repeat Task 2 through Task 6 to continuously improve. | As above …
Task 9: Celebrate success | TBD
Critical Success Factors
1 | Our ability to collaborate between organizations.
2 | Access to ACS resources which implement databases, e-publications, and web presence.
3
4
Barriers to Implementation and Ways To Overcome
1 | Silos within the ACS
2 | Access to ACS resources which implement databases, e-publications, and web presence.
3
4
Resources Needed and Where They Can Be Obtained
1 | Access to ACS resources which implement databases, e-publications, and web presence.
2 | TBD
3
4
Management Accountability
1 | Report to EC
2
3
4
Other Notes
Aligns with Goal 2 of the Envisioning group SP -- collaborate
What about external communication?
LSTs

## G3S1
PROJECT PLAN TEMPLATE
Organizational Unit | Div CHAS
Kickoff Date | 2023-10-01
Goal_3_ | Develop leaders in chemical safety division, the health and safety profession, and the chemistry enterprise.
Goal _3 Strategy _1 | Design and implement a comprehensive leadership development program for CHAS
Impact__Resources__ | Impact H Resources Medium
Target Completion Date | Dec-31-26
Champions | Frankie Wood-Black
Proposed Team Lead | Membership Committee Chair
Other Proposed Team Members | Write Member 1 Here
Write Member 2 Here
Write Member 3 Here
Write Member 4 Here
Write Member 5 Here
Stakeholders Served: | Division and Chemical safety professionals
Target Audiences: | Division and prospective division members, individuals working in the chemical safety profession
Strengths or Opportunities Leveraged: | Knowledge base, expertise, community
Component Task or Decision | Success Metric | Person Responsible | By When
Support and expand graduate student safety workshops | 2 per year, expand to regional meetings | graduate student workshop group | 2026-12-31
Identify and encourage potential CHAS members for leadership opportunities | Increase number of members on subcommittees by 50%, increase number of new symposium organizers by 20%, | Executive Committee, committee chairs, mentors | 2026-12-31
Do a GAP analysis of where CHAS is and where it wants to be
Mentoring of leaders; succession planning
Increase the number of collaborative programming opportunities | At least new technical session with other ACS groups per meeting | Programming committee
Identify 3 new safety speakers for the ACS speakers bureau | New safety speakers | Executive Committee, committee chairs, mentors | 2024-12-31
Identify 1 new ACS Expert | New ACS expert |  | 2024-12-31
Encourage potential CHAS leaders to enroll in the ACS Leadership Program courses (online, on demand, in person). See ACS Institute website. | Completion of ACS Leadership Program Courses by potential CHAS leaders. |  | ongoing
Write Task 7 Here | Write Success Metric for Task 7 Here
Write Task 8 Here | Write Success Metric for Task 8 Here
Critical Success Factors
1
2
3
4
Barriers to Implementation and Ways To Overcome
1
2
3
4
Resources Needed and Where They Can Be Obtained
1 | ACS Institute offerings
2
3
4
Management Accountability
1
2
3
4
Other Notes
Tasks do not appear to align with the G3S1 strategy.
See some of the additions.
Debbie can help
Potential tasks to add to G3S1 (Leadership):
* Identify emerging leaders. Properly document ways to fill in for critical CHAS roles.
* Mentor new leaders. Work with G3S2 project team.
* Provide opportunities for leadership development (i.e. soft skills, career-focused support, etc.)
* Provide constructive feedback
* Teach future mentors how to network
* Offer leadership support

## G3S2
PROJECT PLAN TEMPLATE
Organizational Unit | Div CHAS
Kickoff Date | 2023-10-01
Goal_3_ | Develop leaders in chemical safety division, the health and safety profession, and the chemistry enterprise.
Goal _3 Strategy _2 | Establish a member mentoring program
Impact__Resources__ | Impact H Resources Medium
Target Completion Date | Dec-31-26
Champions | Frankie Wood-Black
Proposed Team Lead | Membership Committee Chair/Executive Committee
Other Proposed Team Members | Write Member 1 Here
Write Member 2 Here
Write Member 3 Here
Write Member 4 Here
Write Member 5 Here
Stakeholders Served: | Division and Chemical safety professionals
Target Audiences: | Division and prospective division members, individuals working in the chemical safety profession
Strengths or Opportunities Leveraged: | Knowledge base, expertise, community
Component Task or Decision | Success Metric | Person Responsible | By When
Identify potential mentors | Create a pool of mentors | Membership Committee | 2024-12-31
For each new Division Member/Young professional - offer potential mentor related to need of individual, e.g. career or topical area. | Create at 10 mentor pairs in the first year. | Membership Committee | 2025-12-31
Identify topic interests of students to support the careers tab on the ACS website to identify Safety/Health Chemistry Careers | 3 new tabs added to the Careers page | Work with Safety Office | 2024-12-31
Write Task 6 Here | Write Success Metric for Task 6 Here
Write Task 7 Here | Write Success Metric for Task 7 Here
Write Task 8 Here | Write Success Metric for Task 8 Here
Critical Success Factors
1 | Getting new volunteers to be mentors
2
3
4
Barriers to Implementation and Ways To Overcome
1
2
3
4
Resources Needed and Where They Can Be Obtained
1
2
3
4
Management Accountability
1
2
3
4
Other Notes
See Chat entries
Jack should be considered to be part of group.
Need further indepth discussion.

## G3S3
PROJECT PLAN TEMPLATE
Organizational Unit | Goal G3S3 Education & Training
Kickoff Date | 2024-01-01
Goal_3_ | Finalize and complete EC review of plan to consolidate all workshops (graduate & professional), webinars, podcasts & other delivery devices under one umbrella for web-site, scheduling, and promotional activities
Goal 3_ Strategy _3 | Implement a "clearing house" for all educational offerings at everiy level. Proposers/sponsors to submit abstract, target audience, medium for delivery, cost information to scheduling center foer posting on the CHAS Calendar.
Impact__Resources__ | Impact, H; Resources, M
Target Completion Date | Write Target Completion Date Here
Champions | Russ Phifer, Kali Miller
Proposed Team Lead | Kali Miller, Russ Phifer
Other Proposed Team Members | Frankie-Wood Black
Melinda Box
Denlinger
Monica Nyansa
Shannon Nephew
Stakeholders Served: | CHAS leadership & Membership
Target Audiences: | Undergrad, grad, post-grad, academic & industrial professionals; all ACS members, non-members with interest in chemical safety
Strengths or Opportunities Leveraged: | Programs are largely already developed
Component Task or Decision | Success Metric | Person Responsible | By When
Develop flow chart showing all types of presentations - workshops, peer-led activities, webinars, podcasts, journal clubs, CHAS chats, safety research, etc. | Completion | Russ/Kali | 2024-01-01
Organize table by type of offering, audience, level of knowledge, and responsible person | Completion | Russ/Kali | 2024-01-01
Hold 1-3 meetings to brainstorm opportunities for new offerings and evaluate current needs in the field that may be missing from the offerings (possibility to gather data about what members need) | Completion and approval by EC | Russ/Kali | 2024-01-01
Propose changes to Admin. Manual & bylaws | Approval by EC and submittal to ACS for bylaws approval | Team | 2024-06-01
Write proposal for EC approval for new organized strategy for offerings (should include a process for making changes or adding/removing offerings) (also, should include a mechanism to integrate all educational offerings from solicitation, development, review, approval, marketing/website, outside promotion) | Completion | Team | 2024-06-01
Develop leadership plan | Completion; submittal as part of Task 3 |  | 2024-01-01
Implement scheduling matrix for website & ACS Safety office promotion | Completion | Team | 2024-03-01
Critical Success Factors
1 | Buy-in by CHAS EC
2
3
4
Barriers to Implementation and Ways To Overcome
1 | Disorganization/ individuals working outside the system
2 | May be a cost to scheduling software; need support from webmaster
3
4
Resources Needed and Where They Can Be Obtained
1 | People! CHAS volunteers
2
3
4
Management Accountability
1
2
3
4
Other Notes
Remove reference to Bylaws
Consider learning outcomes for education offerings.

## Timeline Template
Tasks | 20XX | [11 empty] | 20XX | [11 empty] | 20XX | [11 empty] | 20XX | [11 empty] | 20XX
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
SP Approved
G1S1
G1S2
Sub-task A
Sub-task B
Sub-task C
G1S3
G2S1
Sub-task A
Sub-task B
Sub-task C
G2S2
G2S3
Sub-task A
Sub-task B
Sub-task C
G3S1 | bar: 20XX D
Review
Revisions
Delivery
These elements can be copied and pasted into the timeline as needed
11/1
1/15

## SP Project Timelines
Tasks | 20XX | [11 empty] | 20XX | [11 empty] | 20XX | [11 empty] | 20XX | [11 empty] | 20XX
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
SP Approved
G1S1
G1S2
Sub-task A
Sub-task B
Sub-task C
G1S3
G2S1
Sub-task A
Sub-task B
Sub-task C
G2S2
G2S3
Sub-task A
Sub-task B
Sub-task C
G3S1 | bar: 20XX D
Review
Revisions
Delivery
11/1
1/15
G#S#
Sub-task
G#S#
Sub-task

## Project Charter Template
Project Charter
1. Project Name:
2. Business Case:
3. Problem/Opportunity:
3. Project Team
|  | Name | Telephone | Email
Project Manager:
Team Members:
4. Stakeholders (those having a significant interest in or affected by the project)
5. Project Scope Statement
Project Purpose/Business Justification: (Need this project addresses)
Objectives: (Describe measurable outcomes of the project)
Deliverables: (List high-level "products" to be created)
Scope: (List what will and will not be addressed by the project)
Project Milestones: (Propose start and end dates for Project Phases - Inception, planning, construction, delivery - and other major milestones)
Major Known Risks (including significant Assumptions)
|  | Risk |  |  | Risk Rating (H, M, Lo)
Constraints
External Dependencies
6. Communication Strategy (how project manager will communicate to sponsor, project team members and stakeholders)
7. Sign-off
Sponsors
Project Manager

## Accountability Template
Monthly Status Report |  | [UNIT] Strategic Plan
Date:
Goal 1 |  |  |  | Goal 2: |  |  |  | Goal 3:
Strategy Portfolio | Status |  |  | Strategy Portfolio | Status |  |  | Strategy Portfolio | Status
| Complete | In Progress | Not started |  | Complete | In Progress | Not started |  | Complete | In Progress | Not started
Strategy 1: |  |  |  | Strategy 1: |  |  |  | Strategy 1:
Strategy 2: |  |  |  | Strategy 2: |  |  |  | Strategy 2:
Strategy 3: |  |  |  | Strategy 3: |  |  |  | Strategy 3:
EXAMPLE
Monthly Status Report |  | BMGT Strategic Plan
Date:
Goal 1: Effectively communicate the programs, products, and services of the [Unit] |  |  |  | Goal 2: Provide tangible benefits and opportunities for members to thrive in careers in the chemical enterprise. |  |  |  | Goal 3: Build a clear [Unit] identity that generates awareness and interest, internally and externally
Strategy Portfolio | Status |  |  | Strategy Portfolio | Status |  |  | Strategy Portfolio | Status
| Complete | In Progress | Not started |  | Complete | In Progress | Not started |  | Complete | In Progress | Not started
Strategy 1. Design, develop, and launch a modern and interactive website by [date]. | X |  |  | Strategy 1: Establish a long-term plan for strategic topical programming at [National/Regional/local] meetings |  |  |  | Strategy 1: Perform a complete market analysis (internal and external) to determine who is served and why
Strategy 2. Develop a sustainable communication plan framework to inform Members of [Unit] activities and document in the Procedures Handbook. |  |  |  | Strategy 2: Create a collection of products that give benefits to members with online repository and conduct a gap analysis leading to new benefit ideas |  |  |  | Strategy 2: Develop brand management plan based on G3S1.
Strategy 3. Develop Communications SOP to execute the annual communication plan and raise awareness of BMGT activities |  |  |  | Strategy 3: Develop a program for connecting chemists to essential business skills |  |  |  | Strategy 3: Generate and execute BMTG elevator speech(es) on a consistent basis

## READ ME Tracking Tool
About This Accountability Tracking Tool
The Red Light/Green Light Goal Tracking Tool is for tracking progress toward goal/strategies. This resource contains samples of goals at the organizational, project team, and individual levels. We recommend using it once you’ve finalized your goal/strategies and revisiting at regular intervals (monthly, quarterly, etc.) to check in on progress.
For overall strategic plan leaders, you might use this tool to keep track of your organizational and team goals (using one tab per team!) in one place.
For Project Team Leaders, you can keep track of your team goal/strategy and use separate tabs for each person you manage.
For individuals, use this to keep track of your own goal/strategy (or add a tab for your team goals, for reference).

## Accountability Org Sample
Note: There are multiple sheets within this Accountability tool. Click through the tabs at the bottom of the spreadsheet.
|  | Organizational Goals & Goal Strategies |  |  | Stepback
Priority Area | Goal | Tactics (or Benchmarks / Metrics) | Owner | Current Status | Q1 Update (4/1) | Q2 Update (as of mm/dd) | Q3 Update (as of mm/dd) | Q4 Update (as of mm/dd)
This can be a word (like "Impact") or a sentence ("Be the go-to resource on XYZ issue") that captures what you're trying to achieve with your goals. We recommend limiting the total number of organizational priorities to 5. | Your goal /strategy should be SMARTIE: Strategic, Measurable, Achievable, Realistic, Time-bound, Inclusive, and Equitable. At minimum, your statement should capture the "measurable" and "time | Identify key tactics you will use or benchmarks/metrics you will hit to achieve the goal. If your goal statement alone doesn't capture the "inclusive" and "equitable" aspects of your goal, specify how you're mitigating disparate impact or advancing equity and inclusion in your tactics, benchmarks, or metrics. | The person or team responsible for achieving the goal. Note that organizational goals default to being "owned" by the executive or senior leadership team unless otherwise specified. | On track: Likely to achieve this goal or already completed Not started yet: Have not started making progress yet Not on track: Significantly behind or off track | Indicate when you will review progress quarterly (or monthly or biannually). You can also add columns to indicate benchmarks for each period. Revisit at regular intervals to share updates/progress toward goals.
Sustainability | Raise $2M by end of year to cover this year’s budget and 3 months’ operating reserve. | - Explore option of creating small donor program to engage members from lower-income backgrounds, with a goal of increasing our membership in this demographic by 25% - Apply for 3 new grants and 5 renewals - Explore partnerships with companies that align with our values, particularly around equity, inclusion, and antiracism | Rafael (Development Director) | On track | We have raised $1M to date and are ahead of our pacing.
Impact | Grow the grassroots power of our membership base. By end of year, at least 2,500 people (of which 40% identify as BIPOC) will have been trained through our leadership development programs. At least 80% of participants will answer yes to the statement: "I would recommend this program to a friend." [Cross-listed under Program Team goals] | - Reach out to alumni network for training referrals and nominees - Partner with local organizations to identify potential candidates - Continue building relationship with local HBCU | Anique (Program Director) | Not started yet | We should have enough trainings scheduled in the second half of the year to hit our overall goal, but need to do additional outreach to get to 40% BIPOC.
Impact | Strengthen housing rights coalition and broaden our reach by recruiting 3 local organizations to join by June. These organizations should work with communities that are not currently represented in the coalition. [Cross-listed under Program Team goals] | - Have 1-1s with leaders of community-based organizations - Create 2-pager for coalition recruitment efforts - Host community events for networking and publicity | Anique | On track | Five target organizations have been identified and we've created an outreach and relationship-building plan.
Sustainability | Fill all open roles by June 20xx, with pools for each role having at least XX% BIPOC candidates. | - Host quarterly informational sessions for potential candidates - Join X network and conduct 1-1s to build our pool of candidates and connectors | Mimi (Head of Talent) | Not on track | Program Team hires are going well, but Finance Team hiring hasn't gotten off the ground yet because this year's audit is more complicated than expected. If hiring hasn't started by end of Q2, we may need to adjust the goal or focus on finding temp work to fill gaps.
©The Management Center
Note on E4: we could possibly delete this column if we fold the deadline into the way the goal is written -Monna Wong
Note on F4: to simplify, I think we remove this -- it's a little too close to "current status" -Monna Wong

## Accountability Team Sample
Note: There are multiple sheets within this Accountability tool. Click through the tabs at the bottom of the spreadsheet.
|  | Project Team Goal/Strategy |  |  | Stepback
Priority Area | Goal/Strategy | Tactics (or Benchmarks / Metrics) | Owner | Current Status | Q1 Update (4/1) | Q2 Update (as of mm/dd) | Q3 Update (as of mm/dd) | Q4 Update (as of mm/dd)
Share the organizational priority the goal is connected to. You can also group goals into buckets of work and specify them. For example, if your team's buckets of work include leadership development and partnerships, you could write: "Impact: leadership development." | Your goal /strategy should be SMARTIE: Strategic, Measurable, Achievable, Realistic, Time-bound, Inclusive, and Equitable. At minimum, your statement should capture the "measurable" and "time | Identify key tactics you will use or benchmarks/metrics you will hit to achieve the goal. If your goal statement alone doesn't capture the "inclusive" and "equitable" aspects of your goal, specify how you're mitigating disparate impact or advancing equity and inclusion in your tactics, benchmarks, or metrics. | The person or team responsible for the goal. | On track: Likely to achieve this goal or already completed Not started yet: Have not started making progress yet Not on track: Significantly behind or off track | Indicate when you will review progress quarterly (or monthly or biannually). You can also add columns to indicate benchmarks for each period. Revisit at regular intervals to share updates/progress toward goals.
Impact: Leadership Development | Grow the grassroots power of our membership base. By end of year, at least 2,500 people (of which 40% identify as BIPOC) will have been trained through our leadership development programs. At least 80% of participants will answer yes to the statement: "I would recommend this program to a friend." [Cross-listed under organizational goals] | - Reach out to alumni network for referrals and nominees - Partner with local organizations to identify potential candidates - Continue building relationship with local HBCU | Anique (Program Director) | Not started yet | We should have enough trainings scheduled in the second half of the year to hit our overall goal, but need to do additional outreach to get to 40% BIPOC.
Impact: Partnerships & Coalition | Strengthen housing rights coalition and broaden our reach by recruiting 3 local organizations to join by June. These organizations should work with communities that are not currently represented in the coalition. [Cross-listed under organizational goals] | - Have 1-1s with leaders of community-based organizations - Create 2-pager for coalition recruitment efforts - Host 3 community events to publicize coalition | Anique | On track | Five target organizations have been identified and we've created an outreach and relationship-building plan. | We have connected with three target organizations—2 soft yeses, 1 maybe. Follow-ups have been scheduled.
Sustainability: Capacity | Fill Program Associate vacancy by May 20xx. [As part of organizational goal: Fill all open roles by June 20xx, with pools for each role having at least XX% BIPOC candidates.] | - Reach out to Maria from XYZ network - Reach out to alumni network and identify 5 connectors and/or candidates, of which 80% should be BIPOC. | Jia Ying (Program Manager) | On track | Job announcement shared at end of January—pool is currently at 50% BIPOC, 30% LGBTQ. Just started 2nd round interviews. We may be on track to have new hires begin onboarding by mid-April.
Sustainability | Fill all open roles by June 20xx, with pools for each role having at least XX% BIPOC candidates. | - Host quarterly informational sessions for potential candidates - Join X network and conduct 1-1s to build our pool of candidates and connectors | Mimi (Head of Talent) | Not on track | Program Team hires are going well, but Finance Team hiring hasn't gotten off the ground yet because this year's audit is more complicated than expected. If hiring hasn't started by end of Q2, we may need to adjust the goal or focus on finding temp work to fill gaps.
©The Management Center

## Accountability Indiv. Sample
Note: There are multiple sheets within this Accountability tool. Click through the tabs at the bottom of the spreadsheet.
|  |  | Program Manager Goals |  |  | Stepback
Priority Area | Goal/Strategy | Alignment with team or organizational goal | Tactics (or Benchmarks / Metrics) | Additional Notes (MOCHA, considerations, tasks, etc.) | Current Status | Q1 Update (4/1) | Q2 Update (as of mm/dd) | Q3 Update (as of mm/dd) | Q4 Update (as of mm/dd)
Share the organizational priority the goal is connected to. You can also group goals into buckets of work and specify them. For example, if your team's buckets of work include leadership development and partnerships, you could write: "Impact: leadership development." | Your goal /strategy should be SMARTIE: Strategic, Measurable, Achievable, Realistic, Time-bound, Inclusive, and Equitable. At minimum, your statement should capture the "measurable" and "time | Specify which team or organizational goal your individual goal is connected to. | Identify key tactics you will use or benchmarks/metrics you will hit to achieve the goal. If your goal statement alone doesn't capture the "inclusive" and "equitable" aspects of your goal, specify how you're mitigating disparate impact or advancing equity and inclusion in your tactics, benchmarks, or metrics. | Include any information that will help you achieve your goal, such as the MOCHA (especially helpers, consulteds and approvers), considerations, and important tasks. | On track: Likely to achieve this goal or already completed Not started yet: Have not started making progress yet Not on track: Significantly behind or off track | Indicate when you will review progress quarterly (or monthly or biannually). You can also add columns to indicate benchmarks for each period. Revisit at regular intervals to share updates/progress toward goals.
Impact: Leadership Development | Improve average participant experience scores from 60% highly satisfied to 65% highly satisfied, with no disparities in race or gender. | Organizational/Team goal: Grow the grassroots power of our membership base. By end of year, at least 2,500 people (of which 40% identify as BIPOC) will have been trained through our leadership development programs. At least 80% of participants will answer yes to the statement: "I would recommend this program to a friend." | - Solicit feedback from last year's BIPOC alum on programming logistics through surveys, 1-1s, and focus groups. - Experiment with new platform for participant engagement during the course of the program. - Work with curriculum lead to align curriculum changes with logistical needs. | C: Make sure to have a 1-1 with Lyle. H: Ask Karla for supporting reaching out to some alum. A: Share plan with Anique by Apr 1 | Not started yet | We've solicited feedback, but haven't decided on what changes to test. If we can start testing by May 1, we should be on track to meet this goal.
Impact: Partnerships & Coalition | Recruit members of target organizations to attend at least one of three community events in March. | Organizational/Team goal: Strengthen housing rights coalition and broaden our reach by recruiting 3 local organizations to join by June. These organizations should work with communities that are not currently represented in the coalition. | - Conduct 1-1s with members and staff of target organizations - Reach out to connectors to put in a good word about our work |  | On track |  | We have connected with three target organizations—2 soft yeses, 1 maybe. Follow-ups have been scheduled.
Sustainability: Capacity | Fill Program Associate vacancy by May 20xx. | Organizational goal: Fill all open roles by June 20xx, with pools for each role having at least XX% BIPOC candidates. Team goal: Fill Program Associate vacancy by May 20xx. | - Reach out to Maria from XYZ network - Reach out to alumni network and identify 5 connectors and/or candidates, of which 80% should be BIPOC. | Start tracking potential future talent. Consult with Mimi. | On track | Job announcement shared at end of January—pool is currently at 50% BIPOC, 30% LGBTQ. Just started 2nd round interviews. We may be on track to have new hires begin onboarding by mid-April.
©The Management Center